## Sheet1
Project Name: Walk Tracker
Major tasks
Responsible | Bhanuprakash Thota | Ravi Teja Pagidoju | Gopichand Bandarupalli | Soujanya Janapatla | Sindhu Rani Goli | Navya Devineni | Total Est.Hours
Sprint 1 - RFP
1.1 User Stories | 1 | 1 | 2 | 3 | 1 | 1 | 9
1.3 ER Diagram | 2 | 1 | 2 | 1 | 2 | 1 | 9
1.3 Cost Estimation | 1 | 2 | 2 | 1 | 3 | 2 | 11
1.4 Proposed Screens | 3 | 3 | 1 | 2 | 1 | 2 | 12
1.5 Schedule Management | 1 | 2 | 2 | 1 | 2 | 3 | 11
Sprint 2 - User Development | [6 empty] | 52
2.1 User UI development | 2 | 3 | 2 | 3 | 2 | 4 | 16
2.2 User Database Design | 4 | 2 | 2 | 1 | 4 | 2 | 15
2.3 User Implementation | 3 | 1 | 4 | 2 | 2 | 3 | 15
2.4 User Deploy | 2 | 4 | 3 | 2 | 3 | 2 | 16
Sprint 3 - Admin Development | [6 empty] | 62
3.1 Admin UI development | 2 | 4 | 3 | 3 | 3 | 1
3.2 Admin Database Design | 1 | 1 | 1 | 3 | 2 | 2 | 11
3.3 Admin Implementation | 3 | 2 | 4 | 2 | 3 | 4 | 6
3.4 Admin Deploy | 1 | 1 | 2 | 4 | 1 | 2 | 103.5
Sprint 4 - Admin web Develop | [5 empty] | 30
4.1 Admin webpage UI | 0 | 0 | 2 | 1 | 2 | 5
4.2 Admin BackEnd | 2 | 2 | 1 | 3 | 1 | 9
4.3 Admin Implementation | 0 | 2 | 2 | 1 | 2 | 7
4.4 Admin Deploy | 0 | 1 | 3 | 2 | 3 | 9
Total | 23 | 18 | 31 | 33 | 25 | 130