## Sheet1
Schedule Management
Work Breakdown Structure Categories | Start Date | End Date | Working Hours | Responsible | Estimated Hours per person | [5 empty] | Total Est.Hours
[5 empty] | Bhanu | Ravi | Gopichand | Soujanya | Sindhu | Navya
Initiating | 2020-08-22 | 8/23/2020 |  | Team | 1.5 | 2 | 1.5 | 2 | 1.5 | 1.5 | 10
Planning | 2020-08-23 | 8/24/2020 |  | Team | 2 | 1.5 | 2 | 1.5 | 1.5 | 1 | 9.5
Designing | 2020-08-25 | 11/31/2020 |  | Team | 2 | 1.5 | 1.5 | 1.5 | 2 | 1.5 | 10
UI Design | 2020-08-25 | 9/15/2020 |  | Bhanu | 7 | [5 empty] | 7
Synthesis of Design | 2020-09-16 | 10/15/2020 |  | Team | 1.5 | 1.5 | 2 | 2 | 1.5 | 2 | 10.5
Implementation Iteration | 2020-10-16 | 2020-11-04 |  | Ravi |  | 5 |  |  |  |  | 5
Early release and contract finalization | 2020-11-05 | 11/31/2020 |  | Gopichand |  |  | 6.5 |  |  |  | 6.5
Implementation | 2021-01-20 | 2021-03-30 |  | Team | 1.5 | 1 | 1.5 | 2 | 2 | 2 | 10
Application Development | 2021-01-20 | 2021-02-05 |  | Ravi |  | 6 |  |  |  |  | 6
PWA Implementation | 2021-02-06 | 2021-02-28 |  | Soujanya |  |  |  | 6 |  |  | 6
Android/IOS implementation | 2021-03-01 | 2021-03-30 |  | Sindhu |  |  |  |  | 6 |  | 6
Testing
Monitoring and controlling | 2021-04-03 | 2021-04-17 |  | Team | 2 | 1.5 | 2 | 1.5 | 2 | 2 | 11
Closing | 2021-04-18 | 2021-05-01 |  | Navya | [5 empty] | 6 | 6
Total |  |  |  |  | 17.5 | 20 | 17 | 16.5 | 16.5 | 16 | 103.5