## Sheet1
Cost Estimate
Project name: Walk Tracker
WBS Categories | Team Cost($) | Total time per week(hrs) | Cost per week($) | Total estimated cost(for six sprints)($)
1.Initiating | 431 | 10 | 4310 | 51720
2.Planning | 431 | 9 | 3879 | 46548
3.Designing | 431 | 12 | 5172 | 62064
3.1. Wireframe the UI | - | 3 | - | -
3.2 Combination of design | - | 3 | - | -
3.3.Design Evaluation | - | 3 | - | -
3.4.Claiming and Finalizing contract | - | 3 |  | -
4. Execution | 431 | 11 | 4741 | 56892
4.1. Developing the application | - | 3 | - | -
4.2.PWA implementation | - | 4 | - | -
4.3.Mobile execution | - | 4 | - | -
5. Testing | 431 | 9 | 3879 | 46548
6.Monitoring and Controlling | 431 | 10 | 4310 | 51720
7.Closing | 431 | 9 | 3879 | 46548
Total |  |  |  | 362040
|  | Designation | $/hour
|  | Project Manager | 80
|  | DB Administrator | 75
|  | Team Lead | 72
|  | Quality Assurance | 68
|  | Backend Developer | 68
|  | Frontend Developer | 68