## Sheet1
Project Name: Walk Tracker
Major tasks
Responsible | Bhanuprakash Thota | Ravi Teja Pagidoju | Gopichand Bandarupalli | Soujanya Janapatla | Sindhu Rani Goli | Navya Devineni | Total Est.Hours
Sprint 1 - RFP
1.1 User Stories | 1 | 1 | 2 | 3 | 1 | 1 | 9
1.3 ER Diagram | 2 | 1 | 1 | 1 | 2 | 1 | 8
1.3 Cost Estimation | 1 | 2 | 2 | 1 | 3 | 2 | 11
1.4 Proposed Screens | 3 | 3 | 1 | 2 | 1 | 2 | 12
1.5 Schedule Management | 1 | 2 | 2 | 1 | 1 | 3 | 10
50
Sprint 2 - User Development
2.1 User UI development | 2 | 3 | 1 | 3 | 2 | 3 | 14
2.2 User Database Design | 4 | 2 | 2 | 1 | 3 | 2 | 14
2.3 User Implementation | 3 | 1 | 4 | 2 | 2 | 3 | 15
2.4 User Deploy | 2 | 4 | 3 | 2 | 3 | 2 | 16
59
Sprint 3 - Admin Development
3.1 Admin UI development | 2 | 4 | 3 | 2 | 3 | 1 | 15
3.2 Admin Database Design | 1 | 1 | 1 | 3 | 2 | 2 | 18
3.3 Admin Implementation | 3 | 2 | 3 | 2 | 3 | 3 | 16
3.4 Admin Deploy | 1 | 1 | 2 | 3 | 1 | 2 | 10
60
Sprint 4 - Admin web Develop
4.1 Admin webpage UI | 4 | 3 | 2 | 2 | 1 | 2 | 14
4.2 Admin BackEnd | 2 | 2 | 1 | 3 | 2 | 3 | 13
4.3 Admin Implementation | 1 | 2 | 2 | 2 | 2 | 1 | 10
4.4 Admin Deploy | 2 | 2 | 3 | 2 | 3 | 2 | 14
51
Total | 35 | 36 | 35 | 35 | 35 | 35 | 211